## Worksheet
EXAMPLE BID WORKSHEET (Corresponds to Specification Section 01 10 00 - SUMMARY OF WORK)
The following worksheet is used to make your cost proposal. Quantities presented are estimates only. The Contractor is responsible for verifying all bid quantities. Where quantities are not given, the Contractor must calculate their own. Final quantities utilized for Agreement payment will be from actual field measurement. Items not listed that are required for construction are considered incidental.
City of Greeley, Colorado - Fishing Pond - Addendum 3 Voluntary Cleanup Program Cover Construction
Area of Work |  | Unit | Unit Cost ($) | Engineering Estimated Quantity | As-built Quantity | Estimated Subtotal Cost ($) | Actual Subtotal Cost ($)
BASE BID
General
1 | Mobilization/Demobilization | LS |  | 1 |  | 0 | 0
2 | Performance and Payment Bonds (100%) | LS |  | 1 |  | 0 | 0
3 | Stormwater Control, Dewatering, and Erosion Control (including silt fencing) | LS |  | 1 |  | 0 | 0
4a | Clearing and Grubbing | Acre |  | 4.5 |  | 0 | 0
4b | Debris/Garbage Clean-up and Disposal (southern property boundary and river bank) | LS |  | 1 |  | 0 | 0
4c | Live Tree Removal (Unit Price per tree for live trees not included in general site clearing and grubbing - assume 40'-50' tall) | Each |  | 20 |  | 0 | 0
5 | Subgrade Preparation (Avoid excavation in landfill capping area, proof-roll subgrade, includes concrete rubble disposal) | Acre |  | 4.5 |  | 0 | 0
6 | Construct New Soil CAP (Cover) over landfill in six-inch lifts - minimum 2'-0" and tapered on side-slopes as shown on the Project Drawings | CY |  | 9207 |  | 0 | 0
7 | Purchase and Install 8-oz Geotextile (warning barrier) | SF |  | 111660 |  | 0 | 0
8 | Purchase and Install new 3-Strand Smooth Wire Fencing (specification 32 31 26.13) | LF |  | 1425 |  | 0 | 0
9 | Access Road - approximately 2,208 LF (Includes approximately 1,700 CY Aggregate Surface Course) | LS |  | 1 |  | 0 | 0
10 | Topsoil, Seeding, and Mulching | Acre |  | 3.7 |  | 0 | 0
11a | Selective Pick of Asbestos Containing Concrete | LS |  | 1 |  | 0 | 0
11b | Onsite Concrete Crushing for Reuse | LS |  | 1 |  | 0 | 0
11c | Asbestos disposal (Offsite disposal of stabilized surface piles of Asbestos Containing Materials and Concrete w/ black mastic) * | Truck |  | 1 |  | 0 | 0
Dollars (in words) _________________________________________________________________________________________ |  |  |  |  | TOTAL BASE BID CONSTRUCTION COSTS | 0 | 0
NOTE: Quantities presented in this bid form are estimates only. Contractor is responsible for verifying all bid quantities.
* Price shall be for transport of a tandem size truck of ACM material and includes all loading, unloading, transportation and disposal fees whatsoever. This line item will only be utilized in the event off site transport of material is required.
Equipment Unit Rate (include list of rate schedule for equipment)
The Bidder shall initial one of the following statements: The provided construction schedule and project start time are achievable and acceptable. _________ The provided construction schedule and project start time are not achievable and not acceptable. _________ (Please provide explanation with bid.)
Total Bid (written out):
Vendor Name:
Authorized Signature:
Print Name:
Phone Number:
Email Address: Date: